Program Review Timeline

Year One – Self Study

| FALL SEMESTER | ACTIVITY |
| --- | --- |
| September - December | Program collects and assembles data for self study Program writes self-study report |
| SPRING SEMESTER |  |
| January-March | Program finalizes and submits self-study report |
| April | Self-study report submitted to Dean Program submits names of prospective external reviewers |
| May | Dean submits comments on completeness of the self-study report AVP-PAA and, in the case of graduate programs, DGS approve names of external reviewers Dean of Library and Dean of IITS receive self-study report and may submit responses |

Year Two – Self Study

| FALL SEMESTER | ACTIVITY |
| --- | --- |
| September/October | PAC receives self-study report External Review Team visits campus |
| October/November | External Reviewers submit written report |
| November-January | DC/PD responds to external reviewers’ report Dean responds to the program review package |
| SPRING SEMESTER |  |
| February | PAC reviews program self study, external review, and Dean’s responses |
| March-April | PAC sends its report and recommendations to the AVP_PAA for distribution to DC/PD, Dean, and Provost |
| April | Provost responds to the program review package in preparation for the MOU process |
| April/May | DC/PD, Dean, Provost, and PAC meet to identify priorities and action plan for program improvement, and develop MOU |

Year Three – After the Self Study

| SPRING SEMESTER |  |
| --- | --- |
| January | AVP-PAA reports on program review and changes to Chancellor’s Office (for Board of Trustees) |

# Text boxes

Preparation Activity:  (Activity during the spring semester prior to start of program review):

- AVP-PAA gives formal notification to programs to initiate program review the following fall.

- Programs begin preparation for review:

- Identify data needs

- Appoint self-study coordinator and/or committee

- Continue course and program assessment projects

- OPAA sets up group orientation meeting

- Dean, AVP-PAA and, in the case of graduate programs, DGS, and the chair of PAC review procedures with DC/PD and appropriate faculty

- IPA provides data notebooks