## Slide 1: Project Management
College of Business Administration
Dr. Ishpal Rekhi
2014

## Slide 2: Agenda – Project Management
Introduction
Traditional Approach
Governance Structure
Risks
Work Breakdown Structure
Success Factors
Agile Manifesto
Scrum Methodology

## Slide 3
Those who plan do better than those who do not plan, even though they rarely stick to their plan. ~ Winston Churchill

## Slide 4: Why Project Management?
Have a specific objective to be completed within certain specifications
Have defined start and end dates [Scrum]
Have funding limit
Consume resources
Be multifunctional

## Slide 5: Key Mistakes of Project Management
Clarity on objective
Scope creep
Status report – clarity & purpose
Focus on timeline & budget
Focus on people management
Can management handle the truth?
Sponsorship
Bureaucratic processes

## Slide 6: PM – Traditional Approach [Waterfall]
Initiation
Planning
Execution
Control
Closing
Maintenance
Review project charter
Set initial project objectives and scope
Define project scope
Define project objectives
Define project benefits
Identify sources of business knowledge
Prepare preliminary project timeline
Determine preliminary project costs
Establish business user participation
Identify source of project funding

## Slide 7: PM – Traditional Approach
Initiation
Planning
Execution
Control
Closing
Maintenance
Begin to prepare the project plan
Review goals and objectives
What strategies need to be considered
Identify the specific activities
Definition of each activity
Sequencing of activities
Estimate activity duration
Develop schedule
Develop risk management plan
Determine resource needs
Determine resource costs
Allocate overall cost budget to individual resources
Finalize the project plan

## Slide 8: PM – Traditional Approach
Initiation
Planning
Execution
Control
Closing
Maintenance
Perform the tasks and activities from the plan
Evaluate overall performance to ensure quality standards are being met
Develop individual and team skills to enhance project performance
Distribute project information to stakeholders in a timely manner
Obtain quotes, bids, and offers, or proposals as
needed
Select potential partners and outsource vendors (seller)
Manage the relationship with the seller

## Slide 9: PM – Traditional Approach
Initiation
Planning
Execution
Control
Closing
Maintenance
Coordinate change control across the entire project
Verify the scope
Control changes to the project scope
Control changes to the project schedule
Control changes to the project budget
Monitor specific project results to determine if they comply with relevant quality standards
Disseminate performance information
Monitor and control project risks

## Slide 10: PM – Traditional Approach
Initiation
Planning
Execution
Control
Closing
Maintenance
Closeout all contracts
Administrative closure – generate, gather, and disseminate all information to formalize project completion
Document all lessons learned
Document best practices
Create file system for all project documentation

## Slide 11: PM – Traditional Approach
Initiation
Planning
Execution
Control
Closing
Maintenance
Requirements to continue support in case of issue
Ensuring support – metrics and accountability
Potential enhancements

## Slide 12: Governance Structure
Who is the executive sponsor?
Who is/are the management sponsor?
Who is/are the planning sponsor(s)?
Who is the core team?
Who is the extended team?
Roles and responsibilities

## Slide 13: Project Manager
One point of contact
Manage time, budget and resources
Increase efficiency
Control Scope
Deal with Potential Risks
Administer Procurements
Communicate With Stakeholders
Close the Project

## Slide 14: Skills for a successful PM
Time Management
Organized
Communication
Influencing without authority
Delegation
Pragmatic
Empathetic
Foresight

## Slide 15: Teams
Need for a team – dedicated resources?
  Does the PM select team members?
  Does the PM get assigned team members?
Elements of a successful team
  Knowledge
  Skills
  Attitude
  Team Dynamics
Organization Support
  Inadequate release time
  Territorial behavior (metrics)
  Funding – training & support systems
  Stakeholder commitment

## Slide 16: Tradeoffs
Performance
Cost
Time
P
T
C
Note: = Deviations from original plan
 | Highest | Medium | Lowest
Performance |  |  | 
Cost/Resources |  |  | 
Time |  |  | 

## Slide 17: Risk Mitigation Plan
The alternative to proactive management is reactive management, also called crisis management. This requires significantly more resources and takes longer for problems to surface.
Level of risk is based on the likelihood of the event happening and the expected impact on the project

## Slide 18: Writing Risk Statements
A could happen, which causes B, that would impact C by how much?
Probability of risk [high, medium, low]
What is the magnitude of the impact to the business/customer
Risk Response Strategy
  Accept – low impact risks
  Mitigate – develop a plan for high/medium impact and high/medium probability
  Transfer – transfer the plan to the accountable party and monitor the risk mitigation plan
  Avoid – Change what is required to avoid the risk
Assign owners

## Slide 19: Work breakdown structure (WBS)
Break out the work to as detailed a level as appropriate
Identify owners for each key activity
Identify precedence relationship between the activities
Determine the time required to accomplish each activity

## Slide 20: Project Timeline
Develop the project timeline based for Lodge-Istics Wedding
Gantt Charts

## Slide 21: Communication
Communication needs – Meetings, reports, change orders, conference calls, etc.
Communication Styles – presentations, emails, newsletters, etc.

## Slide 22: Communication
Purpose?
Who is the audience?
Form of communication?
  Email, newsletters, virtual meetings, etc.
Content – what is of interest to this audience?
Seek feedback

## Slide 23: Effective Emails
Subject – What is the purpose? [Action, Inform, etc.]
Email to action item owners [cc the remaining team]
Highlight action items/owners
Align on due dates
Follow-up [use flags as reminders]

## Slide 24: Defining Success
Stakeholder and customer satisfaction
Meeting governance criteria
Meeting business case objectives
Quality of delivery
Customer/end-user adoption
Benefits realization

## Slide 25: Agile Manifesto
We are uncovering better ways of developing software by doing it and helping others do it.
Through this work we have come to value:
Individuals and interactions over processes and tools Working software over comprehensive documentation Customer collaboration over contract negotiation Responding to change over following a plan
That is, while there is value in the items on the right, we value the items on the left more.
http://agilemanifesto.org/

## Slide 26: Scrum versus Waterfall
Probability of success ~ 3X
Probability of failure ~ reduces 3X
Challenged projects – no change

## Slide 27: Scrum and Waterfall - Difference
Fixed Requirements Resources Time
Estimated Resources Time Features
PLAN
FEATURE
Waterfall
Scrum
Waterfall – Requirements perfectly defined, assign resources and time
Scrum – Fixed set of resources and Time, defines and delivers requirements within a time-box

## Slide 28: Scrum Approach
Input from sponsors, stakeholders, users
Product Backlog
Features
Stories
Prioritization
Dependencies
Value
Product Owner
The Team
Team selects what they can deliver within each sprint
Scrum Master
Sprint 1
Sprint 2
Sprint n
Sprint duration decided by team
Breakdown chart
Daily Scrum meeting
Sprint Review
Finished Work
Sprint Retrospective

## Slide 29: Roles in Scrum
Product Owner – Communicates vision of the product, accountable for the product, ensures customer requirements and importance are factored into delivering the product.
Scrum Master – Facilitator for the product owner and team, helps identify and remove obstacles to deliver on the sprint timeline. Focus on productivity.
Team – accountable for delivering the features of the product, determines what can be accomplished within the sprint time

## Slide 30: Scrum Master
Facilitator
Coach
Helps remove impediments
Follow the servant-leader style
Framework custodian

## Slide 31: Success in Scrum
Culture
Leadership
Organization Design
People
Technology

## Slide 32: Weblinks
History of Project Management [video]
PMI Institute
Agile Manifesto
Scrum Methodology